## Project Data
Project Publication Schedule
Project Name | Unfolding of Languages | USE THIS SHEET TO INTRODUCE THE PROJECT DATES THE FILE WILL THEN CALCULATE ALL THE PUBLICATION DATES ACCORDINGLY
Project Code | 2020-1-HU01-KA105-077820
Project Start | 2022-01-01
Mobility Start | 2022-06-01
Mobility End | 2022-06-10
Project End | 2023-01-01
January | 2022
February | 2023
March | 2024
April | 2025
May | 2026
June | 2027
July | 2028
August | 2029
September | 2030
October | 2031
November | 2032
December | 2033
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: change dates here

## Publication dates (hidden)
Date | Type of Post | Platform | Description
2022-01-31 | Text+Banner | FB; DSCD | 1-Announce your project
2022-04-02 | Promotional Banner+Call to Action | FB; IG; DSCD | 2-Opening of participant selection
2022-04-22 | Photos and text / Teaser Video + Call to action (links) | FB; IG; DSCD | 3-Mid-way of participant selection
2022-04-22 | Newsletter/Message + Call to Action (links) | Mailing List | 3-Mid-way of participant selection
2022-05-17 | Photos and Text | FB; IG; DSCD | 4-End of participant selection
2022-06-01 | Photos+Text+Story/Reel | FB; IG | 5-Mobility 1
2022-06-02 | Story/Reel | FB; IG | 5-Mobility 2
2022-06-03 | Photos+Text+Story/Reel | FB; IG | 5-Mobility 3
2022-06-04 | Story/Reel | FB; IG | 5-Mobility 4
2022-06-05 | Photos+Text+Story/Reel | FB; IG | 5-Mobility 5
2022-06-06 | Story/Reel | FB; IG | 5-Mobility 6
2022-06-07 | Photos+Text+Story/Reel | FB; IG | 5-Mobility 7
2022-06-08 | Story/Reel | FB; IG | 5-Mobility 8
2022-06-09 | Photos+Text+Story/Reel | FB; IG | 5-Mobility 9
2022-06-10 | Story/Reel | FB; IG | 5-Mobility 10
2022-06-10 | Recap Video | YT (FB); IG | 6-Project Video
2022-06-15 | Photos (100) | FB | 7-Project Photo Album
2022-07-10 | Photos/Videos/Stories of mobility | FB; IG | 9-Throwback 1
2022-07-25 | Photos/Videos/Stories of mobility | FB; IG | 9-Throwback 2
2022-08-09 | Photos of Events (various posts untill this date) | FB; IG | 8-Dissemination
2022-08-09 | Photos/Videos/Stories of mobility | FB; IG | 9-Throwback 3
2022-08-24 | Photos/Videos/Stories of mobility | FB; IG | 9-Throwback 4
2023-01-01 | Photos+Text | FB; IG | 10-Project Closure
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Text Photo+Text Project Banner Teaser Video Newsletter

## Calendar
Month | Year |  | ← CHANGE MONTH HERE |  |  |  | Project - Unfolding of Languages - 2020-1-HU01-KA105-077820
December | 2022
2022-12-01 | [6 empty] | Number of Posts this month - 0 |  |  |  | 2022-12-01 | 2022-12-31
M | T | W | T | F | S | S | Date | Type of Post | Platform | Description
2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04
2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11
2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18
2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25
2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31 | 2023-01-01
2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Text Photo+Text Project Banner Teaser Video Newsletter